## Slide 1
Kimpton Memorial Hall
Solar Panel Installation

## Slide 2: HISTORY
Considered in 2013
Insufficient funds
Lack of enthusiasm

## Slide 3: Why Now?
Email from village resident to Hall trustees
Rising fuel costs
Greening Kimpton
Money in the bank

## Slide 4: Timeline March to November 2022
Inverter installed
System commissioned and working
MARCH
APRIL/MAY
JULY
AUGUST
OCTOBER
NOVEMBER
Fact finding – advice from Tim H-S about possible grant source.
2 potential companies selected
Site visits and quotes
Investigation of possible grants
Roof inspection to assess suitability
Grant from Low Carbon Workspace approved
Roof inspection results to Building Control for Building Regulations approval
Proposal approved by trustees
Application for Permitted Lawful Development submitted to NHDC
Solinvictus commissioned to install system
Solar panels installed

## Slide 5: BENEFITS
Investment paid back within 5 years
Doing our bit for a greener Kimpton & the environment
Reduced electricity bills*
Income from selling unused electricity to National Grid
*Initial estimate = £2,500 saving per year (before fuel costs increased)

## Slide 6
Solinvictus appointed August
Earliest mutually convenient start date October 3rd.
No new daytime booking taken for the agreed week
Installers worked round existing bookings
1 week to install everything except inverter**
Inverter installed 4 weeks later
System fully operational 7th November
**Delay due to worldwide shortage of inverters
Installation Process

## Slide 7
38 panels
Installation Complete

## Slide 8: The Inverter

## Slide 9
New additions to the ‘electricity cupboard’.

## Slide 10
Building inspection £650
Lawful Development Application £263
Installation of system £16,686
Total £17,599
Low Carbon Workspace grant £ 5,000
Total cost to Hall £12,599
Costs

## Slide 11
Barbara Kazwini
Booking Secretary
Kimpton Memorial Hall
Hall Lane,
Kimpton.
Herts.
SG4 8RD
www.kimptonmemorialhall.co.uk